## Sheet1
ID: | Tasks: | Dates: | 09/08 - 09/17 | 09/17 - 09/27 | 09/27 - 10/11 | 10/11 - 10/18 | 10/18 - 10/20 | 10/20 - 11/1 | 11/1 - 11/5 | 11/5 - 11/19 | 11/19 - 12/13 | 12/13 -12/18 | 12/18 - 12/20 | 12/20 - 2/15 | 2/15 - 3/18 | 3/18 - 5/15
2.1.1 | Team Contracts | [13 empty] | KEY
2.1.2 | System Boundary Diagram (SBD) | [13 empty] | Critical Path =
2.1.3 | Mission Scenario Diagram (MSD) | [13 empty] | Path =
2.1.4 | Five + Five Key Spec
2.1.5 | TSR01
2.1.6 | Gantt Chart & Network Diagram
2.1.7 | TSR02
2.1.8 | System Requirement Specification (SRS) Draft
2.1.9 | System Requirement Review
2.1.10 | Statement of Work (SOW) Draft
2.1.11 | TSR03
2.1.12 | TSR04
2.1.13 | TSR05
2.1.14 | Preliminary Design Review
2.1.15 | Prototype Demonstrations
2.1.16 | Statement of Work (SOW) Final
2.1.17 | System Requirement Specification (SRS) Final
2.1.18 | Critical Design Review (CDR)
2.1.19 | Final Demonstrations
2.2.1 | Preliminary Equipment Research
2.2.2 | Drone & Equipment List Draft
2.2.3 | Drone & Equipment List Final
2.2.4 | Purchase Drones and Equipment
2.2.5 | Define Headers, Libraries & Frameworks
2.2.6 | Develop Structural Software Design
2.2.7 | Configure Transciever Intercommunication
2.2.8 | Implement Wireless LED Control
2.2.9 | Implement Wireless Drone Control
2.2.10 | Implement Flight Route Automation
2.2.11 | Merge LED Control & Route Automation Code
2.2.12 | Secure Lighting Display to Drones
2.3.1 | Perform Self-Test for Wireless Comms.
2.3.2 | Perform LED Control Tests
2.3.3 | Perform Flight Automation Tests
2.3.4 | Verify Flight Route & Manipulation